## Sheet1
|  |  | Week # | Milestones
|  |  | Week 1 | Looking for Partner / Learn Java
|  |  | Week 2 | Project plan / Learn Java and BitBucket / Java assignment
|  |  | Week 3 | Finishing off Java assignment / Start on GUI
|  |  | Week 4 | Work on GUI and start implementing game logic
|  |  | Week 5 | Continue working on game logic and AI implementation
|  |  | Week 6 | AI and multiplayer implementations / Extra features / Graphics
|  |  | Week 7 | 4 page Report / Phase 1 interview preparation / Finalising 'combat' game
|  |  | Break | Learning Python during the break
|  |  | Week 8 | Learn Python / Finish off the Python Assignment
|  |  | Week 9 | Working on class protocols, cooperating with classmates
|  |  | Week 10 | Implementation of in-game communication system
|  |  | Week 11 | Implementation of Web interfaces
|  |  | Week 12 | Additional features including databases or efficiency of P2P
|  |  | Week 13 | Preparation of phase 2 individual interview / 8 page report
Risk / Challenge | Description of the risk / challenge | Mitigation / Solution
Time Management | There will be possible hardship due to having projects from other courses e.g. ENGGEN 303 (SYSTEMS). | To prevent losing control of our time management, completing assignments as soon as it comes out and starting on projects asap will greatly help.
New Language | Learning Java and Python for the first time within the strict timeframe could be challenging. | Going through the tutorials online during our own time will help us learn new languanges a lot faster. Referring back to the lecture slides will also be useful.
Partner Cooperation | Difference in specialisation of our team members could have timetable differences, causing hard to meet up. | Having each other timetable and working around it would be the only option here. Meeting up in the evenings/night after all classes would be preferable.
Ideas (features/design) | Coming up with unique but innovative ideas will be quite challenging, especially none of us play games often. | Any brainstorm ideas can drop down on paper while thinking about new features and designs. Playing games could also help us get that "Eureka" moment.
Programming level | The level of programming could differ between us as our backgrounds are different. | To overcome one person 'carrying' the other person, we can learn and discuss about the language, also motivate each other to finish the project together.
Lack of Computers | Sometimes, there are no free computers used for this we might not have a place to work on the project. | In these cases, working on our own laptops could really come in handy. Bringing our laptops everyday would be essential to not be affected by such situation.